| Title: Magee, OL 202 Assignment One - Logframe Template to Fill In |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Student Date: Date of Student Assignment Here |  |  |  |  |  |  |
| OL 202 Assignment One Student Logframe Template to Fill In - Annotated |  |  |  |  |  |  |
| 500 families will enjoy improved nutrition & food security through a community garden, food surplus donations & a client choice food pantry program. |  |  |  |  |  |  |
| Problem Statement | [Problems and underlying causes] 1,000 small children from 500 families in four cities surrounding Claremont, California, (1) suffer a lack of access to sufficient fruits, vegetables, and meat products due to a lack of a place for raising their own vegetables and a lack of a program for collecting surplus food from restaurants and grocery stores. (2) They also suffer from an inability to choose their weekly food products from food pantries due to a lack of knowledge of family nutrition for better stocking the food pantries and in making healthy choices in the selection of food. These challenges contribute to [Negative Impacts] (a) families suffering from food insecurity and a lack of food diversity that reduces (b) their children's ability to concentrate in school (c) and also reduces the ability of adults to lead the productive, meaningful, prosperous lives they need to leave the cycle of poverty. |  |  |  |  |  |
|  |  |  |  | Objectively Verifiable Indicators | Means of Verification |  |
| Goal [Short-term and medium–term outcomes of the activities/outputs/sub-goals of the project] | 1,000 small children from 500 families in four cities surrounding Claremont, California, will [Underlying causes to problems as if they have been solved] (1) have access to sufficient fruits, vegetables, and meat products through a community garden program and through a restaurant, and grocery store donation program. (2) They will also enjoy better family nutrition and the ability to individually choose their food allotment through a client choice food pantry program. These opportunities contribute to [Positive Impacts] (a) family food security and food diversity. These opportunities also improve (b) their children's ability to concentrate in school (c) and also improve the ability of adults to lead the productive, meaningful, prosperous lives they need to leave the cycle of poverty. |  |  |  |  |  |
|  |  |  |  | [Long-term positive outcome] Impact |  |  |
| (1) Sub-Goal 1 (Objective) [sub-components of the main goal, which when added together describe the main goal] |  |  |  |  |  |  |
| Community garden program | [Short-term positive outcome influencing mid-term positive outcome] 50% of 1,000 small children from 500 families in four cities surrounding Claremont will be able to have access to sufficient fruits and vegetables through a community garden program |  |  | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] |  |  |
| Output 1.1 [sub-components of the sub-goal, which when added together describe the sub-goal] | Form a community garden team which includes staff members, volunteers, and community members to assess feasibility and develop a plan. |  |  |  |  |  |
|  | Activity 1.1.1 | Solicit recommendations for members of the garden team; hold a meeting and meet with interested parties |  |  |  |  |
|  | Activity 1.1.2 | Discuss the purpose of the team and ask volunteers. Select final team members. |  |  |  |  |
|  | Activity 1.1.3 | Assess individual capabilities and interests |  |  |  |  |
|  | Activity 1.1.4 | Assign team member groups and duties |  |  |  |  |
| Output 1.2 [sub-components of the sub-goal, which when added together describe the sub-goal] | Research different community garden programs, and visit local community gardens |  |  |  |  |  |
|  | Activity 1.2.1 | Conduct Internet research on different kinds of community garden programs |  |  |  |  |
|  | Activity 1.2.2 | Research local community gardens in Claremont and surrounding communities |  |  |  |  |
|  | Activity 1.2.3 | Analyze and compare the most appropriate national programs to programs available to visit in the greater Claremont area |  |  |  |  |
|  | Activity 1.2.4 | Visit the most appropriate community gardens near to Claremont and arrange meetings with organizers for ideas that would work our organization |  |  |  |  |
| Output 1.3 [sub-components of the sub-goal, which when added together describe the sub-goal] | Research potential garden plot locations. |  |  |  |  |  |
|  | Activity 1.3.1 | Contact local cities and institutions that may have parcels of land community gardens available |  |  |  |  |
|  | Activity 1.3.2 | Report to board with findings and recommendation; request preliminary board approval |  |  |  |  |
|  | Activity 1.3.3 | Re-contact the city your institution with board recommendation and discuss project implementation |  |  |  |  |
| Output 1.4 [sub-components of the sub-goal, which when added together describe the sub-goal] | 10% of 500 families participated in a survey to gauge interest and also to better understand the things they would like to grow |  |  |  |  |  |
|  | Activity 1.4.1 | Develop a survey designed to gather information about community member interest and types of things they would like to grow |  |  |  |  |
|  | Activity 1.4.2 | Work with volunteers and community garden team members to present the survey to community members |  |  |  |  |
|  | Activity 1.4.3 | Tabulate results of the survey |  |  |  |  |
| Output 1.5 [sub-components of the sub-goal, which when added together describe the sub-goal] | Work with a nutritionist to determine feasibility, appropriate crops – and develop a simple gardening and nutrition workshop. |  |  |  |  |  |
|  | Activity 1.5.1 | Identify a nutritionist willing to partner on the project and make an appointment |  |  |  |  |
|  | Activity 1.5.2 | Present findings from community survey |  |  |  |  |
|  | Activity 1.5.3 | Ask nutritionist to identify nutritionally sound food crops a can be grown in a garden |  |  |  |  |
|  | Activity 1.5.4 | Compare nutritionist's list to survey list and develop a finalized list of things request as donations |  |  |  |  |
| Output 1.6 [sub-components of the sub-goal, which when added together describe the sub-goal] | Develop or revise a detailed plan (logframe), budget, and timeframe for launching the community garden program. |  |  |  |  |  |
|  | Activity 1.6.1 | Develop or revise a detailed log frame for the community garden project |  |  |  |  |
|  | Activity 1.6.2 | Develop or revise a detailed budget for the community garden project |  |  |  |  |
|  | Activity 1.6.3 | Develop or revise a detailed timeframe for the community garden project |  |  |  |  |
|  | Activity 1.6.4 | Present detailed log frame, budget and timeframe to the board for preliminary approval |  |  |  |  |
| Output 1.7 [sub-components of the sub-goal, which when added together describe the sub-goal] | Assess funding possibilities. |  |  |  |  |  |
|  | Activity 1.7.1 | Send newsletter to existing donor base proposing a gala at the potential community garden site |  |  |  |  |
|  | Activity 1.7.2 | Organize the gala and ask for volunteers to assist in preparation and manning the gala |  |  |  |  |
|  | Activity 1.7.3 | Gala with existing donor bases held at the potential community garden site |  |  |  |  |
|  | Activity 1.7.4 | Send newsletter to existing donor base with highlights of the gala and a donation request |  |  |  |  |
|  | Activity 1.7.5 | Determine whether donations from this initial donor request is an indication that there sufficient interest for funding the project |  |  |  |  |
|  | Activity 1.7.6 | Make a list of other key players that can provide funding and in-kind services such as community-based organizations, foundations, or cities and institutions |  |  |  |  |
| Output 1.8[sub-components of the sub-goal, which when added together describe the sub-goal] | 20% of 500 families participated in workshops and follow-up in family nutrition and home garden planning for nutrition and follow up for 3 months |  |  |  |  |  |
|  | Activity 1.8.1 | Develop workshop lesson plan; collect/develop workshop materials |  |  |  |  |
|  | Activity 1.8.2 | Arrange workshop meetings with communities |  |  |  |  |
|  | Activity 1.8.3 | Present workshops |  |  |  |  |
|  | Activity 1.8.4 | Provide 3 months follow-up |  |  |  |  |
| Output 1.9 [sub-components of the sub-goal, which when added together describe the sub-goal] | 20% of 500 families participated in workshops on forming beds and planting seeds and follow-up for 3 months |  |  |  |  |  |
|  | Activity 1.9.1 | Develop workshop lesson plan; collect/develop workshop materials |  |  |  |  |
|  | Activity 1.9.2 | Arrange workshop meetings with communities |  |  |  |  |
|  | Activity 1.9.3 | Present workshops |  |  |  |  |
|  | Activity 1.9.4 | Provide 3 months follow-up |  |  |  |  |
| (2) Sub-Goal 2 (Objective) [sub-components of the main goal, which when added together describe the main goal] |  |  |  |  |  |  |
| Restaurant and Grocery Store Surplus Food Donation Program [sub-components of the sub-goal, which when added together describe the sub-goal] | [Short-term positive outcome influencing mid-term positive outcome] 50% of 500 families in four cities surrounding Claremont will be able to have access to sufficient fruits, vegetables, and meat products through a restaurant, and grocery store donation program. |  |  | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] |  |  |
| Output 2.1 | Form a Restaurant and Grocery Store Donation team (which includes staff members, volunteers, and community members) to assess feasibility and develop a plan |  |  |  |  |  |
|  | Activity 2.1.1 | Solicit recommendations for members of the restaurant, and grocery store team; hold a meeting and meet with interested parties |  |  |  |  |
|  | Activity 2.1.2 | Discuss the purpose of the team and ask volunteers. Select final team members. |  |  |  |  |
|  | Activity 2.1.3 | Assess individual capabilities and interests |  |  |  |  |
|  | Activity 2.1.4 | Assign team member groups and duties |  |  |  |  |
| Output 2.2 | Research different restaurant and grocery store donation programs and visit local food pantries, restaurant and grocery stores participating in program |  |  |  |  |  |
|  | Activity 2.2.1 | Conduct Internet research on different kinds of restaurant and grocery store programs |  |  |  |  |
|  | Activity 2.2.2 | Research local restaurant and grocery store programs in Claremont and surrounding communities |  |  |  |  |
|  | Activity 2.2.3 | Analyze and compare the most appropriate national programs to programs available to visit in the greater Claremont area |  |  |  |  |
|  | Activity 2.2.4 | Visit the most appropriate potential restaurants and grocery stores near to Claremont and arrange meetings with organizers for ideas that would work our organization |  |  |  |  |
| Output 2.3[sub-components of the sub-goal, which when added together describe the sub-goal] | Research product availability, transportation, pickup and delivery, and manpower requirements. |  |  |  |  |  |
|  | Activity 2.3.1 | Contact 3 restaurants and grocery stores that may have potential donations available |  |  |  |  |
|  | Activity 2.3.2 | Discuss with restaurant and grocery store staff transportation, pickup and delivery, and manpower requirements |  |  |  |  |
|  | Activity 2.3.3 | Report to board with findings and recommendation; request preliminary board approval |  |  |  |  |
|  | Activity 2.3.4 | Re-contact the restaurants and grocery stores with board recommendation and discuss project implementation |  |  |  |  |
| Output 2.4 | 10% of 500 families participated in a survey to gauge interest and also to better understand the things they would enjoy from a program such as this |  |  |  |  |  |
|  | Activity 2.4.1 | Develop a survey designed to gather information about community member interest and types of things they would enjoy from a program such as this |  |  |  |  |
|  | Activity 2.4.2 | Work with volunteers and restaurant and grocery store team members to present the survey to community members |  |  |  |  |
|  | Activity 2.4.3 | Tabulate results of the survey |  |  |  |  |
|  | Activity 2.4.4 | Provide 3 months follow-up |  |  |  |  |
| Output 2.5 | Work with a nutritionist to better understand a healthy diversity of products identified by restaurants and grocery stores |  |  |  |  |  |
|  | Activity 2.5.1 | Identify a nutritionist willing to partner on the project and make an appointment |  |  |  |  |
|  | Activity 2.5.2 | Present findings from community survey |  |  |  |  |
|  | Activity 2.5.3 | Ask nutritionist to identify nutritionally sound and safe food supplies that could be donated by restaurants and grocery stores |  |  |  |  |
|  | Activity 2.5.4 | Compare nutritionist's list to survey list and develop a finalized list of things to solicit as donations |  |  |  |  |
| Output 2.6 [sub-components of the sub-goal, which when added together describe the sub-goal] | Use this information to determine feasibility and develop a detailed working plan, budget and timeframe. |  |  |  |  |  |
|  | Activity 2.6.1 | Develop or revise a detailed log frame for the restaurant and grocery store program |  |  |  |  |
|  | Activity 2.6.2 | Develop or revise a detailed budget for the restaurant and grocery store program |  |  |  |  |
|  | Activity 2.6.3 | Develop or revise a detailed timeframe for the restaurant and grocery store program |  |  |  |  |
|  | Activity 2.6.4 | Present detailed log frame, budget and timeframe to the board for plenary approval |  |  |  |  |
| Output 2.7 | Assess funding possibilities |  |  |  |  |  |
|  | Activity 2.7.1 | Send newsletter to existing donor base proposing a gala at the potential restaurant and grocery store program |  |  |  |  |
|  | Activity 2.7.2 | Organize the gala and ask for volunteers to assist in preparation and manning the event |  |  |  |  |
|  | Activity 2.7.3 | Gala with existing donor bases held at a potential grocery store |  |  |  |  |
|  |  | Send newsletter to existing donor base with highlights of the gala and a donation request |  |  |  |  |
|  | Activity 2.7.4 | Determine whether donations from this initial donor request is an indication that there sufficient interest for funding the project |  |  |  |  |
|  | Activity 2.7.5 | Make a list of other key players that can provide funding and in-kind services such as community-based organizations, foundations, or cities and institutions |  |  |  |  |
| Output 2.8 [sub-components of the sub-goal, which when added together describe the sub-goal] | Fine-tune the restaurant and grocery store program based upon the consultancies and interviews and officially launch a simplified 60 day pilot program |  |  |  |  |  |
|  | Activity 2.8.1 | Develop a transportation, pickup, delivery and volunteer schedule |  |  |  |  |
|  | Activity 2.8.2 | Have a final meeting with restaurant and grocery store contacts to clarify details |  |  |  |  |
|  | Activity 2.8.3 | Pick up first weekly donation and deliver to food bank |  |  |  |  |
|  | Activity 2.8.4 | Evaluate first pick up and delivery and fine tune program |  |  |  |  |
|  | Activity 2.8.5 | Evaluate first 30 days pilot program |  |  |  |  |
|  | Activity 2.8.6 | Evaluate pilot program prior to full program launch |  |  |  |  |
| (3) Sub-Goal 3 (Objective) [sub-components of the main goal, which when added together describe the main goal] |  |  |  |  |  |  |
| Client Choice Food Pantry program [sub-components of the sub-goal, which when added together describe the sub-goal] | [Short-term positive outcome influencing mid-term positive outcome] 50% of 1,000 small children from 500 families in four cities surrounding Claremont will be able to enjoy better family nutrition and the ability to individually choose their food allotment through a client choice food pantry program |  |  | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] |  |  |
| Output 3.1 | Set up a Client Choice team (with one staff member, one volunteer and one community client) to research feasibility and develop a plan for the Client Choice Program |  |  |  |  |  |
|  | Activity 3.1.1 | Solicit recommendations for members of the Client Choice team; hold a meeting and meet with interested parties |  |  |  |  |
|  | Activity 3.1.2 | Discuss the purpose of the team and ask volunteers. Select final team members. |  |  |  |  |
|  | Activity 3.1.3 | Assess individual capabilities and interests |  |  |  |  |
|  | Activity 3.1.4 | Assign team member groups and duties |  |  |  |  |
| Output 3.2 | 10% of 500 families participated in a survey to gain a better understanding of community member food preferences. |  |  |  |  |  |
|  | Activity 3.2.1 | Develop a survey designed to gather information about community member interest and types of things they would like to grow |  |  |  |  |
|  | Activity 3.2.2 | Work with volunteers and community garden team members to present the survey to community members |  |  |  |  |
|  | Activity 3.2.3 | Tabulate results of the survey |  |  |  |  |
| Output 3.3[sub-components of the sub-goal, which when added together describe the sub-goal] | Work with a nutritionist to fill in gaps in the list and to develop a simple family nutrition workshop for community members and staff alike. |  |  |  |  |  |
|  | Activity 3.3.1 | Identify a nutritionist willing to partner on the project and make an appointment |  |  |  |  |
|  | Activity 3.3.2 | Present findings from community survey |  |  |  |  |
|  | Activity 3.3.3 | Compare the food gaps to the programs above to determine feasibility in filling the gaps. |  |  |  |  |
|  | Activity 3.3.4 | Ask nutritionist to identify nutritionally sound food choices |  |  |  |  |
|  | Activity 3.3.5 | Compare nutritionist's list to survey list and develop a finalized list |  |  |  |  |
| Output 3.4 | Use this information to determine feasibility and develop a detailed working plan, budget and timeframe. |  |  |  |  |  |
|  | Activity 3.4.1 | Develop or revise a detailed log frame for the client choice program |  |  |  |  |
|  | Activity 3.4.2 | Develop or revise a detailed budget for the client choice program |  |  |  |  |
|  | Activity 3.4.3 | Develop or revise a detailed timeframe for the client choice program |  |  |  |  |
|  | Activity 3.4.4 | Develop or revise a detailed log frame for the client choice program |  |  |  |  |
| Output 3.5 [sub-components of the sub-goal, which when added together describe the sub-goal] | 20% of 500 families participated in workshops and follow-up in family nutrition and client choice planning for nutrition and follow up for 3 months. |  |  |  |  |  |
|  | Activity 3.5.1 | Develop workshop lesson plan; collect/develop workshop materials |  |  |  |  |
|  | Activity 3.5.2 | Arrange workshop meetings with communities |  |  |  |  |
|  | Activity 3.5.3 | Present workshops |  |  |  |  |
|  | Activity 3.5.4 | Provide 3 months follow-up |  |  |  |  |
| Output 3.6 [sub-components of the sub-goal, which when added together describe the sub-goal] | Fine-tune the client choice program based upon the tests and officially launch a simplified 60 day pilot program |  |  |  |  |  |
|  | Activity 3.6.1 | Develop an organizational and volunteer schedule |  |  |  |  |
|  | Activity 3.6.2 | Have a final meeting with team to clarify details |  |  |  |  |
|  | Activity 3.6.3 | Lay out first client choice food choices |  |  |  |  |
|  | Activity 3.6.4 | Evaluate first client choice event and fine tune program |  |  |  |  |
|  | Activity 3.6.5 | Evaluate first 30 days pilot program |  |  |  |  |
|  | Activity 3.6.6 | Evaluate pilot program prior to full program launch |  |  |  |  |

Copyright Tim Magee