| Title: Magee, OL 202 Assignment Two - Logframe Template to Fill In |
| --- |
| Student Date: Date of Student Assignment Here |
| OL 202 Assignment Two Student Logframe Template to Fill In - Annotated |
| 500 families will enjoy improved nutrition & food security through a community garden, food surplus donations & a client choice food pantry program. |
| Problem Statement | [Problems and underlying causes] 1,000 small children from 500 families in four cities surrounding Claremont, California, (1) suffer a lack of access to sufficient fruits, vegetables, and meat products due to a lack of a place for raising their own vegetables and a lack of a program for collecting surplus food from restaurants and grocery stores. (2) They also suffer from an inability to choose their weekly food products from food pantries due to a lack of knowledge of family nutrition for better stocking the food pantries and in making healthy choices in the selection of food. These challenges contribute to [Negative Impacts] (a) families suffering from food insecurity and a lack of food diversity that reduces (b) their children's ability to concentrate in school (c) and also reduces the ability of adults to lead the productive, meaningful, prosperous lives they need to leave the cycle of poverty. |
|  |  |  |  | Objectively Verifiable Indicators | Means of Verification |  |
| Goal [Short-term and medium–term outcomes of the activities/outputs/sub-goals of the project] | 1,000 small children from 500 families in four cities surrounding Claremont, California, will [Underlying causes to problems as if they have been solved] (1) have access to sufficient fruits, vegetables, and meat products through a community garden program and through a restaurant, and grocery store donation program. (2) They will also enjoy better family nutrition and the ability to individually choose their food allotment through a client choice food pantry program. These opportunities contribute to [Positive Impacts] (a) family food security and food diversity. These opportunities also improve (b) their children's ability to concentrate in school (c) and also improve the ability of adults to lead the productive, meaningful, prosperous lives they need to leave the cycle of poverty. |
|  |  | [Long-term positive outcome] Impact | 1,000 small children from 500 families in four cities surrounding Claremont, California have sufficient food and better nutrition and lead healthy, prosperous, productive lives. |
| (1) Sub-Goal 1 (Objective) [sub-components of the main goal, which when added together describe the main goal] |
| Community garden program | [Short-term positive outcome influencing mid-term positive outcome] 50% of 1,000 small children from 500 families in four cities surrounding Claremont will be able to have access to sufficient fruits and vegetables through a community garden program | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] | 1,000 small children from 500 families adopt a family gardening into their lives allowing children to grow and develop properly, be able to participate in education, and be prosperous, productive members of their communities. |
| Output 1.1 [sub-components of the sub-goal, which when added together describe the sub-goal] | Form a community garden team which includes staff members, volunteers, and community members to assess feasibility and develop a plan. | Staff and community members will learn to come together as a program planning team | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 1.1.1 | Solicit recommendations for members of the garden team; hold a meeting and meet with interested parties | Solicitation prepared; meeting organized and held | Printed copy of solicitation and responses; copy of attendance and meeting schedule – or photos |  |
|  | Activity 1.1.2 | Discuss the purpose of the team and ask volunteers. Select final team members. | Prepare plan for the meeting | Copy of team list |  |
|  | Activity 1.1.3 | Assess individual capabilities and interests | Prepare survey | Copy of survey |  |
|  | Activity 1.1.4 | Assign team member groups and duties | Prepare group list | Copy of group list too much I can |  |
| Output 1.2 [sub-components of the sub-goal, which when added together describe the sub-goal] | Research different community garden programs, and visit local community gardens | Community garden team learn about different types of garden programs and be able to report back to the organization | Research notes and field staff notes and photos |  |
|  | Activity 1.2.1 | Conduct Internet research on different kinds of community garden programs | 20 community garden websites plus 10 community garden studies have been researched | Printed copies of most viable programs and studies |  |
|  | Activity 1.2.2 | Research local community gardens in Claremont and surrounding communities | 10 community garden websites have been researched | Printed copies of most viable programs and studies |  |
|  | Activity 1.2.3 | Analyze and compare the most appropriate national programs to programs available to visit in the greater Claremont area | The five most appropriate national programs have been compared to five local community gardens | Copy of one page report on the comparison |  |
|  | Activity 1.2.4 | Visit the most appropriate community gardens near to Claremont and arrange meetings with organizers for ideas that would work our organization | Three local community gardens have been identified, visited and staff meetings have been held | Name and addresses of three community gardens, field staff notes on visits and meetings, and photos |  |
| Output 1.3 [sub-components of the sub-goal, which when added together describe the sub-goal] | Research potential garden plot locations. | Potential, accessible garden plot locations have been identified—and cost for gaining access clearly described | Name and addresses of three potential garden plot locations, field staff notes on visits and meetings, and photos; report on costs. |  |
|  | Activity 1.3.1 | Contact local cities and institutions that may have parcels of land community gardens available | 10 cities and institutions have been approached about parcels of land | Name and addresses of three cities are institutions with potential garden plot locations, field staff notes on visits and meetings, and photos; report on costs |  |
|  | Activity 1.3.2 | Report to board with findings and recommendation; request preliminary board approval | The board has been appraised of potential parcels of land and recommendations; the board has voted on the most appropriate option | Copy of report to board, board minutes, and photos |  |
|  | Activity 1.3.3 | Re-contact the city your institution with board recommendation and discuss project implementation | The city or institution has been approached with an initial approval and project implementation is been discussed | Copy of report to city or institution and a report of their response |  |
| Output 1.4 [sub-components of the sub-goal, which when added together describe the sub-goal] | 10% of 500 families participated in a survey to gauge interest and also to better understand the things they would like to grow | 100 families participate in a survey and express their level of interest and what they would like to grow | Copy of an analysis report of survey |  |
|  | Activity 1.4.1 | Develop a survey designed to gather information about community member interest and types of things they would like to grow | Survey prepared | Copy of survey |  |
|  | Activity 1.4.2 | Work with volunteers and community garden team members to present the survey to community members | Community garden team members and volunteers presented the survey to 100 community members | Copy of survey results |  |
|  | Activity 1.4.3 | Tabulate results of the survey | The results of the survey were tabulated | Copy of report on survey tabulation |  |
| Output 1.5 [sub-components of the sub-goal, which when added together describe the sub-goal] | Work with a nutritionist to determine feasibility, appropriate crops – and develop a simple gardening and nutrition workshop. | 100 families and the community garden team members learn the nutritional benefits of a community garden program | Copy of report, field staff notes and photos |  |
|  | Activity 1.5.1 | Identify a nutritionist willing to partner on the project and make an appointment | A nutritionist has been identified and an appointment made | Name of nutritionist and date of appointment |  |
|  | Activity 1.5.2 | Present findings from community survey | The nutritionist was presented with the results of the community garden survey | Copy of report on the results of the community garden survey |  |
|  | Activity 1.5.3 | Ask nutritionist to identify nutritionally sound food crops a can be grown in a garden | The nutritionist identified necessary a nutritious crops can be grown in a community garden | Copy of the list of crops |  |
|  | Activity 1.5.4 | Compare nutritionist's list to survey list and develop a finalized list of things request as donations | The nutritionist list was compared to the community members list and appropriate finalized list was developed | Copy of finalized crop list for the community garden |  |
| Output 1.6 [sub-components of the sub-goal, which when added together describe the sub-goal] | Develop or revise a detailed plan (logframe), budget, and timeframe for launching the community garden program. | A detailed plan, budget, and timeframe for launching the community garden program has been developed or revised. | Copy of detailed plan, budget, timeframe |  |
|  | Activity 1.6.1 | Develop or revise a detailed log frame for the community garden project | A detailed log frame was completed | Copy of the detailed log frame |  |
|  | Activity 1.6.2 | Develop or revise a detailed budget for the community garden project | A detailed budget was completed | Copy of the detailed budget |  |
|  | Activity 1.6.3 | Develop or revise a detailed timeframe for the community garden project | A detailed timeframe was completed | Copy of the detailed timeframe |  |
|  | Activity 1.6.4 | Present detailed log frame, budget and timeframe to the board for preliminary approval | The board has been appraised of the detailed plan, budget, and timeframe; the board has voted on the most appropriate option | Copy of report to board, board minutes, and photos |  |
| Output 1.7 [sub-components of the sub-goal, which when added together describe the sub-goal] | Assess funding possibilities. | A survey of potential funding opportunities has been assessed | Copy of funding assessment |  |
|  | Activity 1.7.1 | Send newsletter to existing donor base proposing a gala at the potential community garden site | Content for newsletter was prepared; newsletter was sent | Copy of newsletter and report on opening click through rates |  |
|  | Activity 1.7.2 | Organize the gala and ask for volunteers to assist in preparation and manning the gala | The gala was organized and volunteers selected | Copy of attendance ; copy of schedule |  |
|  | Activity 1.7.3 | Gala with existing donor bases held at the potential community garden site | 100 potential donors attended the gala | Notes from field staff, quotes from existing donor base, photos with donors |  |
|  | Activity 1.7.4 | Send newsletter to existing donor base with highlights of the gala and a donation request | Content for newsletter was prepared; newsletter was sent | Copy of newsletter and report on opening click through rates. Report on donations received. |  |
|  | Activity 1.7.5 | Determine whether donations from this initial donor request is an indication that there sufficient interest for funding the project | The report was generated indicating the level of donor interest and funds raised | Copy of report |  |
|  | Activity 1.7.6 | Make a list of other key players that can provide funding and in-kind services such as community-based organizations, foundations, or cities and institutions | A list of key potential donors has been developed | Copy of lists |  |
| Output 1.8[sub-components of the sub-goal, which when added together describe the sub-goal] | 20% of 500 families participated in workshops and follow-up in family nutrition and home garden planning for nutrition and follow up for 3 months | 100 families learn the health benefits and techniques of planning and utilizing home gardens for family nutrition and adopt it for 12 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 1.8.1 | Develop workshop lesson plan; collect/develop workshop materials | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 1.8.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of sign-up sheet; copy of schedule |  |
|  | Activity 1.8.3 | Present workshops | Members of 100 families attend workshops on hand washing | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 1.8.4 | Provide 3 months follow-up | Families visited once a month for 3 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| Output 1.9 [sub-components of the sub-goal, which when added together describe the sub-goal] | 20% of 500 families participated in workshops on forming beds and planting seeds and follow-up for 3 months | 100 families prepare and plant home gardens for family nutrition and adopt it for 6 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 1.9.1 | Develop workshop lesson plan; collect/develop workshop materials | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 1.9.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of sign-up sheet; copy of schedule |  |
|  | Activity 1.9.3 | Present workshops | Members of 100 families attend workshops on planting gardens | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 1.9.4 | Provide 3 months follow-up | Families visited once a month for 6 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| (2) Sub-Goal 2 (Objective) [sub-components of the main goal, which when added together describe the main goal] |
| Restaurant and Grocery Store Surplus Food Donation Program [sub-components of the sub-goal, which when added together describe the sub-goal] | [Short-term positive outcome influencing mid-term positive outcome] 50% of 500 families in four cities surrounding Claremont will be able to have access to sufficient fruits, vegetables, and meat products through a restaurant, and grocery store donation program. | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] | 50% of 500 families in four cities surrounding Claremont adopt good overall nutrition and food security practices into their lives through a restaurant, and grocery store donation program allowing children to grow and develop properly and be able to participate in education, and be prosperous, productive members of their communities. |
| Output 2.1 | Form a Restaurant and Grocery Store Donation team (which includes staff members, volunteers, and community members) to assess feasibility and develop a plan | Staff and community members will learn to come together as a program planning team | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 2.1.1 | Solicit recommendations for members of the restaurant, and grocery store team; hold a meeting and meet with interested parties | Solicitation prepared; meeting organized and held | Printed copy of solicitation and responses; copy of attendance and meeting schedule – or photos |  |
|  | Activity 2.1.2 | Discuss the purpose of the team and ask volunteers. Select final team members. | Prepare plan for the meeting | Copy of team list |  |
|  | Activity 2.1.3 | Assess individual capabilities and interests | Prepare survey | Copy of survey |  |
|  | Activity 2.1.4 | Assign team member groups and duties | Prepare group list | Copy of group list too much I can |  |
| Output 2.2 | Research different restaurant and grocery store donation programs and visit local food pantries, restaurant and grocery stores participating in program | Restaurant and grocery store team learn about different types of donation programs and be able to report back to the organization | Research notes and field staff notes and photos |  |
|  | Activity 2.2.1 | Conduct Internet research on different kinds of restaurant and grocery store programs | 20 restaurants and grocery store program websites plus 10 restaurant and grocery store program studies have been researched | Printed copies of most viable programs and studies |  |
|  | Activity 2.2.2 | Research local restaurant and grocery store programs in Claremont and surrounding communities | 5 local restaurant and grocery store program websites have been researched | Printed copies of most viable programs and studies |  |
|  | Activity 2.2.3 | Analyze and compare the most appropriate national programs to programs available to visit in the greater Claremont area | The five most appropriate national programs have been compared to five local programs | Copy of one page report on the comparison |  |
|  | Activity 2.2.4 | Visit the most appropriate potential restaurants and grocery stores near to Claremont and arrange meetings with organizers for ideas that would work our organization | Three local potential restaurants and grocery stores have been identified, visited and staff meetings have been held | Name and addresses of three potential restaurants and grocery stores, field staff notes on visits and meetings, and photos |  |
| Output 2.3[sub-components of the sub-goal, which when added together describe the sub-goal] | Research product availability, transportation, pickup and delivery, and manpower requirements. | Potential, restaurants and grocery stores have been identified—and product availability, transportation, pickup and delivery, and manpower requirements clearly described | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 2.3.1 | Contact 3 restaurants and grocery stores that may have potential donations available | 3 restaurants and grocery stores have been approached about potential donations | Copy of report on three potential restaurants and grocery stores, field staff notes on visits and meetings, and photos. |  |
|  | Activity 2.3.2 | Discuss with restaurant and grocery store staff transportation, pickup and delivery, and manpower requirements | Transportation, pickup and delivery, and manpower requirements has been discussed with restaurant and grocery store staff | Copy of report on discussions, field staff notes on visits and meetings, and photos. |  |
|  | Activity 2.3.3 | Report to board with findings and recommendation; request preliminary board approval | The board has been appraised of potential restaurants and grocery stores and recommendations; the board has voted on the most appropriate option | Copy of report to board, board minutes, and photos |  |
|  | Activity 2.3.4 | Re-contact the restaurants and grocery stores with board recommendation and discuss project implementation | The restaurants and grocery stores have been approached with an initial approval and project implementation is been discussed | Copy of report to restaurants and grocery stores and a report of their response |  |
| Output 2.4 | 10% of 500 families participated in a survey to gauge interest and also to better understand the things they would enjoy from a program such as this | 100 families participate in a survey and express their level of interest and what they would enjoy from a program such as this | Copy of an analysis report of survey |  |
|  | Activity 2.4.1 | Develop a survey designed to gather information about community member interest and types of things they would enjoy from a program such as this | Survey prepared | Copy of survey |  |
|  | Activity 2.4.2 | Work with volunteers and restaurant and grocery store team members to present the survey to community members | Community restaurant, and grocery store team members and volunteers presented the survey to 100 community members | Copy of survey results |  |
|  | Activity 2.4.3 | Tabulate results of the survey | The results of the survey were tabulated | Copy of report on survey tabulation |  |
|  | Activity 2.4.4 | Provide 3 months follow-up | Families visited once a month for 3 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| Output 2.5 | Work with a nutritionist to better understand a healthy diversity of products identified by restaurants and grocery stores | 100 families and the restaurant and grocery store team members learn the nutritional benefits of a restaurant and grocery store donation program | Copy of report, field staff notes, and photos |  |
|  | Activity 2.5.1 | Identify a nutritionist willing to partner on the project and make an appointment | A nutritionist has been identified and an appointment made | Name of nutritionist and date of appointment |  |
|  | Activity 2.5.2 | Present findings from community survey | The nutritionist was presented with the results of the community survey of the types of things they would enjoy from a program such as this | Copy of report on the results of the community survey |  |
|  | Activity 2.5.3 | Ask nutritionist to identify nutritionally sound and safe food supplies that could be donated by restaurants and grocery stores | The nutritionist identified nutritionally sound and safe food supplies that could be donated by restaurants and grocery stores | Copy of the list of potential food supply donations |  |
|  | Activity 2.5.4 | Compare nutritionist's list to survey list and develop a finalized list of things to solicit as donations | The nutritionist list was compared to the community members list and appropriate finalized list was developed | Copy of finalized food donations for the community garden |  |
| Output 2.6 [sub-components of the sub-goal, which when added together describe the sub-goal] | Use this information to determine feasibility and develop a detailed working plan, budget and timeframe. | A detailed plan, budget, and timeframe for launching the community garden program has been developed or revised. | Copy of detailed plan, budget, timeframe |  |
|  | Activity 2.6.1 | Develop or revise a detailed log frame for the restaurant and grocery store program | A detailed log frame was completed | Copy of the detailed log frame |  |
|  | Activity 2.6.2 | Develop or revise a detailed budget for the restaurant and grocery store program | A detailed budget was completed | Copy of the detailed budget |  |
|  | Activity 2.6.3 | Develop or revise a detailed timeframe for the restaurant and grocery store program | A detailed timeframe was completed | Copy of the detailed timeframe |  |
|  | Activity 2.6.4 | Present detailed log frame, budget and timeframe to the board for plenary approval | The board has been appraised of the detailed plan, budget, and timeframe; the board has voted on the most appropriate option | Copy of report to board, board minutes, and photos |  |
| Output 2.7 | Assess funding possibilities | A survey of potential funding opportunities has been assessed | Copy of funding assessment |  |
|  | Activity 2.7.1 | Send newsletter to existing donor base proposing a gala at the potential restaurant and grocery store program | Content for newsletter was prepared; newsletter was sent | Copy of newsletter and report on opening click through rates |  |
|  | Activity 2.7.2 | Organize the gala and ask for volunteers to assist in preparation and manning the event | The gala was organized and volunteers selected | Copy of attendance ; copy of schedule |  |
|  | Activity 2.7.3 | Gala with existing donor bases held at a potential grocery store | 100 potential donors attended the gala | Notes from field staff, quotes from existing donor base, photos with donors |  |
|  |  | Send newsletter to existing donor base with highlights of the gala and a donation request | Content for newsletter was prepared; newsletter was sent | Copy of newsletter and report on opening click through rates. Report on donations received. |  |
|  | Activity 2.7.4 | Determine whether donations from this initial donor request is an indication that there sufficient interest for funding the project | The report was generated indicating the level of donor interest and funds raised | Copy of report |  |
|  | Activity 2.7.5 | Make a list of other key players that can provide funding and in-kind services such as community-based organizations, foundations, or cities and institutions | A list of key potential donors has been developed | Copy of lists |  |
| Output 2.8 [sub-components of the sub-goal, which when added together describe the sub-goal] | Fine-tune the restaurant and grocery store program based upon the consultancies and interviews and officially launch a simplified 60 day pilot program | A simplified 60 day pilot program for the restaurant and grocery store program based has been launched | Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 2.8.1 | Develop a transportation, pickup, delivery and volunteer schedule | Transportation, pickup, delivery and volunteer schedule prepared | Copy of transportation, pickup, delivery and volunteer schedule |  |
|  | Activity 2.8.2 | Have a final meeting with restaurant and grocery store contacts to clarify details | A final meeting with restaurant and grocery store contacts to clarify details was held | Copy of meeting notes |  |
|  | Activity 2.8.3 | Pick up first weekly donation and deliver to food bank | First weekly donation and delivery to food bank accomplished | Copy of pick up and delivery documents |  |
|  | Activity 2.8.4 | Evaluate first pick up and delivery and fine tune program | The first pick up and delivery was evaluated and the program fine-tuned | Copy of evaluation notes |  |
|  | Activity 2.8.5 | Evaluate first 30 days pilot program | The first 30 days of pick up and delivery were evaluated and the program fine-tuned | Copy of evaluation notes |  |
|  | Activity 2.8.6 | Evaluate pilot program prior to full program launch | The pilot program was evaluated prior to full program launch | Copy of evaluation notes |  |
| (3) Sub-Goal 3 (Objective) [sub-components of the main goal, which when added together describe the main goal] |
| Client Choice Food Pantry program [sub-components of the sub-goal, which when added together describe the sub-goal] | [Short-term positive outcome influencing mid-term positive outcome] 50% of 1,000 small children from 500 families in four cities surrounding Claremont will be able to enjoy better family nutrition and the ability to individually choose their food allotment through a client choice food pantry program | Outcome [Medium-term positive outcome leading to long-term positive outcome (Impact)] | 50% of 500 families in four cities surrounding Claremont adopt good overall nutrition and food security practices into their lives through a client choice program allowing children to grow and develop properly and be able to participate in education, and be prosperous, productive members of their communities. |
| Output 3.1 | Set up a Client Choice team (with one staff member, one volunteer and one community client) to research feasibility and develop a plan for the Client Choice Program | Staff and community members will learn to come together as a client choice planning team | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 3.1.1 | Solicit recommendations for members of the Client Choice team; hold a meeting and meet with interested parties | Solicitation prepared; meeting organized and held | Printed copy of solicitation and responses; copy of attendance and meeting schedule – or photos |  |
|  | Activity 3.1.2 | Discuss the purpose of the team and ask volunteers. Select final team members. | Prepare plan for the meeting | Copy of team list |  |
|  | Activity 3.1.3 | Assess individual capabilities and interests | Prepare survey | Copy of survey |  |
|  | Activity 3.1.4 | Assign team member groups and duties | Prepare group list | Copy of group list |  |
| Output 3.2 | 10% of 500 families participated in a survey to gain a better understanding of community member food preferences. | 100 families participate in a survey and express their level of interest and what they would like to grow | Copy of an analysis report of survey |  |
|  | Activity 3.2.1 | Develop a survey designed to gather information about community member interest and types of things they would like to grow | Survey prepared | Copy of survey |  |
|  | Activity 3.2.2 | Work with volunteers and community garden team members to present the survey to community members | Community garden team members and volunteers presented the survey to 100 team members | Copy of survey results |  |
|  | Activity 3.2.3 | Tabulate results of the survey | The results of the survey were tabulated | Copy of report on survey tabulation |  |
| Output 3.3[sub-components of the sub-goal, which when added together describe the sub-goal] | Work with a nutritionist to fill in gaps in the list and to develop a simple family nutrition workshop for community members and staff alike. | 100 families learn the health benefits and techniques of planning and utilizing home gardens for family nutrition and adopt it for 12 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 3.3.1 | Identify a nutritionist willing to partner on the project and make an appointment | A nutritionist has been identified and an appointment made | Name of nutritionist and date of appointment |  |
|  | Activity 3.3.2 | Present findings from community survey | The nutritionist was presented with the results of the community garden survey | Copy of report on the results of the community garden survey |  |
|  | Activity 3.3.3 | Compare the food gaps to the programs above to determine feasibility in filling the gaps. | The nutritionist identified food gaps | Copy of the list of food gaps |  |
|  | Activity 3.3.4 | Ask nutritionist to identify nutritionally sound food choices | The nutritionist identified necessary sound food choices | Copy of the sound food choices |  |
|  | Activity 3.3.5 | Compare nutritionist's list to survey list and develop a finalized list | The nutritionist list was compared to the community members list and appropriate finalized list was developed | Copy of finalized list |  |
| Output 3.4 | Use this information to determine feasibility and develop a detailed working plan, budget and timeframe. | A detailed plan, budget, and timeframe for launching the community garden program has been developed or revised. | Copy of detailed plan, budget, timeframe |  |
|  | Activity 3.4.1 | Develop or revise a detailed log frame for the client choice program | A detailed log frame was completed | Copy of the detailed log frame |  |
|  | Activity 3.4.2 | Develop or revise a detailed budget for the client choice program | A detailed budget was completed | Copy of the detailed budget |  |
|  | Activity 3.4.3 | Develop or revise a detailed timeframe for the client choice program | A detailed timeframe was completed | Copy of the detailed timeframe |  |
|  | Activity 3.4.4 | Develop or revise a detailed log frame for the client choice program | A detailed log frame was completed | Copy of the detailed log frame |  |
| Output 3.5 [sub-components of the sub-goal, which when added together describe the sub-goal] | 20% of 500 families participated in workshops and follow-up in family nutrition and client choice planning for nutrition and follow up for 3 months. | 100 families learn the health benefits of a client choice program family nutrition and adopt it for 6 months | Copy of sign-in sheets and photos of the workshops; Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 3.5.1 | Develop workshop lesson plan; collect/develop workshop materials | Lesson plan prepared, workshop materials collected | Printed copy of lesson plan, delivery or purchase receipts of materials – or photos |  |
|  | Activity 3.5.2 | Arrange workshop meetings with communities | Prospective attendees filled in sign-up sheets for workshops & schedules prepared | Copy of sign-up sheet; copy of schedule |  |
|  | Activity 3.5.3 | Present workshops | Members of 100 families attend workshops on hand washing | Copy of sign-in sheets and photos of the workshops |  |
|  | Activity 3.5.4 | Provide 3 months follow-up | Families visited once a month for 3 months after workshops | Copy of signed visit sheets, field staff notes, schedule and photos |  |
| Output 3.6 [sub-components of the sub-goal, which when added together describe the sub-goal] | Fine-tune the client choice program based upon the tests and officially launch a simplified 60 day pilot program | A simplified 60 day pilot program for the client choice program based has been launched | Copy of signed visit sheets, field staff notes, schedule and photos |  |
|  | Activity 3.6.1 | Develop an organizational and volunteer schedule | Organizational and volunteer schedule prepared | Copy of organizational and volunteer schedule |  |
|  | Activity 3.6.2 | Have a final meeting with team to clarify details | A final meeting with team to clarify details was held | Copy of meeting notes |  |
|  | Activity 3.6.3 | Lay out first client choice food choices | First weekly client choice event accomplished | Copy of pickup and delivery documents |  |
|  | Activity 3.6.4 | Evaluate first client choice event and fine tune program | The first client choice event was evaluated and the program fine-tuned | Copy of evaluation notes |  |
|  | Activity 3.6.5 | Evaluate first 30 days pilot program | The first 30 days of the program were evaluated and the program fine-tuned | Copy of evaluation notes |  |
|  | Activity 3.6.6 | Evaluate pilot program prior to full program launch | The pilot program was evaluated prior to full program launch | Copy of evaluation notes |  |