| Student Title: Magee, OL 241 Assignment Six Student Simple Logframe Template to Fill In – Annotated |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Student Date: Date of Student Assignment Here |  |  |  |  |  |  |
| 3,200 townspeople in Willcox, Arizona will be able to enjoy replenished water supplies and reduced heat. |  |  |  |  |  |  |
| https://training.csd-i.org/climate-change-action-plan-global-warming-climate-challenges/ |  |  |  |  |  |  |
| Problem Statement | [Problems and underlying causes] 3200 townspeople and their businesses in Willcox, Arizona, are suffering from 1) diminishing water supplies due to A) climate related droughts and B) heavy, rapidly flowing runoff from surrounding agricultural fields and mountains caused by extreme weather events not charging groundwater, and 2) global warming induced heat waves magnified by C) very little shade in neighborhoods and in the downtown area. These challenges are causing [Negative Impacts] (a) dry wells for homeowners and negative economic impacts to farms and ranches, and b) businesses suffering from reduced tourism dollars. Combined, these challenges c) reduce the ability of families to lead the productive, meaningful, prosperous lives they desire and to be able to contribute to the continued development of their community. |  |  |  |  |  |
| Goal Statement | 3,200 townspeople and their businesses in Willcox, Arizona, will be able to enjoy [Underlying causes to problems as if they have been solved] (1) replenished water supplies through a Groundwater Recharge Program and 2) heat waves reduced through a Street Tree Program These opportunities contribute to leading to [Positive Impacts] a) working wells for homeowners and positive economic impacts for farms and ranches, and b) businesses enjoying renewed tourism dollars. Combined, these programs will c) increase the ability of families to lead the productive, meaningful, prosperous lives they desire and to be able to contribute to the continued development of their community. |  |  |  |  |  |
| (1) Sub-Goal 1 (Objective) [sub-components of the main goal, which when added together describe the main goal] |  |  |  |  |  |  |
| Groundwater Recharge Program to Replenish Water | 3,200 Willcox townspeople and their businesses will be able to enjoy replenished water supplies through Groundwater Recharge Program |  |  |  |  |  |
| Output 1.1 | Survey with community members to identify their knowledge of local water use |  |  |  |  |  |
| Output 1.2 | Consultation with a hydraulic engineer to help develop the scope of the project |  |  |  |  |  |
| Output 1.3 | Community workshop on participatory mapping of water resources |  |  |  |  |  |
| Output 1.4 | Prioritize water springs, rivulets, ravines and man-made waterways for protection/restoration |  |  |  |  |  |
| Output 1.5 | Investigate scientifically proven groundwater recharging techniques |  |  |  |  |  |
| Output 1.6 | Work with the hydraulic engineer to develop a project design with activities, a budget, a schedule and necessary funding documents |  |  |  |  |  |
| Output 1.7 | Present the plan to community members for comment |  |  |  |  |  |
| Output 1.8 | Develop a multifaceted funding plan: federal, state, county, foundation, and private funding |  |  |  |  |  |
| (2) Sub-Goal 2 (Objective) [sub-components of the main goal, which when added together describe the main goal] |  |  |  |  |  |  |
| Street Tree Program to Reduce Urban Heat | Willcox businesses will enjoy renewed tourism dollars shade producing Street Tree Program |  |  |  |  |  |
| Output 2.1 | Survey with community members to identify their knowledge of urban trees |  |  |  |  |  |
| Output 2.2 | Consultation with an arborist with street tree experience to help develop scope of the project |  |  |  |  |  |
| Output 2.3 | Community workshop on participatory mapping of a street tree plan |  |  |  |  |  |
| Output 2.4 | Prioritize locations for tree planting |  |  |  |  |  |
| Output 2.5 | Investigate scientifically proven techniques and species for urban tree plantings for reducing urban heat in a semiarid region |  |  |  |  |  |
| Output 2.6 | Work with the arborist to develop a project design with activities, a budget, a schedule and necessary funding documents |  |  |  |  |  |
| Output 2.7 | Present the plan to community members for comment |  |  |  |  |  |
| Output 2.8 | Develop a multifaceted funding plan: federal, state, county, foundation, and private funding |  |  |  |  |  |

Copyright © Tim Magee